## Sheet1
Progress | Category | PWS Task Code | Work Title | Work Timeframe | Start Date | End Date | Duration (Days) | Goal | Current Status | Value Provided | Timeline to Completion | Est Completion Notes | Status | Completion % | Days Remaining | Project Validity
0.5 | Outreach & Engagement | 5.5.7.1 - Support the data, analytics, and AI competency development and work role refresh. Create competency models for data, analytics, and AI. Leverage developed competencies to inform Work Role (KSAT) updates. | Digital Workforce Initiative Memorandum Development | 06/2023 - 01/2024 | 2023-06-01 | 2024-01-01 | 214 | Formalize and communicate the strategy for classifying and managing the digital workforce. | Completed; Delivered to CDAO Leadership 11/2023, Published January 2024 | Provided a standardized framework for classifying and managing the Department's digital workforce, enabling strategic workforce planning, resource allocation, and data-driven decision-making related to data, AI, and software engineering roles. This ultimately improves the Department's ability to leverage its digital talent for mission success. | Long Term (6+ Months) | 50% - Need DoD Components to complete coding workforce with Data/AI Work Roles | Long Term | 0.5 | 0 | Completed
0.9 | Data | 5.5.7.1 - Support the data, analytics, and AI competency development and work role refresh. Create competency models for data, analytics, and AI. Leverage developed competencies to inform Work Role (KSAT) updates. | Criticality Analysis Validation & Data Review | 06/2023 - 11/2023 | 2023-06-01 | 2023-11-01 | 1 | Ensure accurate and consistent classification of Data/AI roles across the organization | Completed; Participated in 8+ SME Sessions from 06/2023 - 10/2023. Reviewed data from 10/2023 - 11/2023. Published results 11/2023. | Ensured accurate and consistent classification of Data/AI roles by validating data, reconciling methodological discrepancies, and identifying core tasks. This improved classification supports effective workforce planning and resource allocation for data and AI initiatives. | Completed - Requires periodic updates and maintenance | 90% - Need to complete Work Role Refresh prior to conducting Criticality Analysis | Completed | 0.9 | 0 | Completed
0.7 | Outreach & Engagement | 5.5.7.3 - Collaborate with appropriate stakeholders to organize and execute Digital Talent Management Forum. | Functional Community Manager Roadshow Development and Delivery | 06/2023 - 12/2023 | 2023-06-01 | 2023-12-01 | 1 | Secure buy-in and understanding of the new governance model from stakeholders across the organization. | Completed; Draft provided to GPOC 08/2023; incorporated review 09/2023 - 10/2023. Provided Final version 12/2023 to CDAO Leadership. Need updates dire | Secured stakeholder buy-in and understanding of the CDAO's work role coding initiative and governance model, fostering collaboration and ensuring smooth implementation across the organization. This shared understanding promotes consistent application and maximizes the value of the initiative. | Completed - Needs Review and Approval | 70% - Need to update, review and approve presentation. Schedule multiple virtual/in-person briefings regarding Governance | Completed | 0.7 | 0 | Completed
0.95 | Outreach & Engagement | 5.5.7.3 - Collaborate with appropriate stakeholders to organize and execute Digital Talent Management Forum. | Alternative of Analysis for Digital Talent Management Forum | 04/2024 - 12/2024 | 2024-04-01 | 2024-12-01 | 1 | Strengthen the DoD's digital talent pipeline by improving the impact and relevance of the Digital Talent Management Forum. | Completed; Conducted analysis of attendee list and past briefings from 04/2024 - 06/2024; Presented results to the GPOC on 07/2024. Requested by DTM to do additional analysis on 09/2024. 12/2024 effort put on Strategic Pause | Strengthened the DoD's digital talent pipeline by improving the forum's effectiveness, relevance, and impact. Streamlining processes and modernizing content will ensure the forum better addresses current and future digital talent needs. | Completed - Needs Review and Approval | 95% - Need review of analysis and next steps from GPOC | Completed | 0.95 | 0 | Completed
0.8 | Policy | 5.5.7.2 - Create, iterate, and publish guidance materials for the data/AI and work role coding guide. | 8140 Policy Enhancement & CDAO Authority Definition | 06/2023 - 01/2024 | 2023-06-01 | 2024-01-01 | 1 | Formalize the CDAO's authority and responsibilities in managing the digital workforce. | Completed; Reviewed 8140 Policy 06/2023 - 08/2023. Provided line by line edits to GPOC 09/2023. Incorporated additional edits 10/2023. In-person meeting with CIO held 11/2023. No further leadership engagement post 11/2023 meeting. | Formalized the CDAO's authority and responsibilities regarding the digital workforce, enabling effective leadership, management, and development of this critical talent pool. This strengthens the Department's ability to leverage its digital expertise for mission success. | Completed - Needs Review and Approval | 80% - Need to coordinate proposed changes with CIO, R&E, and WHS | Completed | 0.8 | 0 | Completed
1 | Outreach & Engagement | 5.5.7.3 - Collaborate with appropriate stakeholders to organize and execute Digital Talent Management Forum. | CDAO DTM "Big Plays" Pilot Program | 06/2023 - 01/2024 | 2023-06-01 | 2024-01-01 | 1 | Improve work-role coding accuracy and drive data-driven workforce planning for data/AI talent. Success metrics include increased buy-in, process improvement, coding accuracy, and robust data tracking. | Completed; Developed interview scripts and questions 06/2023 - 08/2023; Conducted 20+ interviews with DFAS from 08/2023 - 11/2023; Analyzed data using sentiment analysis 11/2023 - 12/2023; Final Report provided to GPOC 01/2024. | Improved data coding accuracy and work role buy-in, while also informing a newly published work role coding guide for consistent HR data, creating a scalable model for a robust talent pipeline. | Completed | 1 | Completed | 1 | 0 | Completed
0.8 | Work Role Coding / Competencies | 5.5.7.2 - Create, iterate, and publish guidance materials for the data/AI and work role coding guide. | Work Role Coding Guide for Data, AI, and Software Engineering - Development & Publication | 06/2024 - 11/2024 | 2024-06-01 | 2024-11-01 | 153 | Provide clear guidance and standardized procedures for coding and classifying Data/AI work roles. | Version 1 Completed. Internally and externally validated and delivered to GPOC 10/2024. Incorporate feedback 10/2024 and final version published 11/2024 Version 2 Initiated 12/2024 - 04/2024, Repeated updated and internal validation to evaluate and reflect user feedback, evolving work role code alignment to occupational codes | Provided standardized procedures and clear guidance for classifying Data/AI and Software Engineering roles, improving coding accuracy, consistency, and efficiency for enhanced workforce planning and data-driven decision-making. | Completed - Requires periodic updates and maintenance | 80% - Requires iterative updates as CIO and R&E modify Work Roles and as processes change. | Completed | 0.8 | 0 | Completed
0.95 | Work Role Coding / Competencies | 5.5.7.1 - Support the data, analytics, and AI competency development and work role refresh. Create competency models for data, analytics, and AI. Leverage developed competencies to inform Work Role (KSAT) updates. | DA&AI Work Role Vignettes | 08/2023 - 10/2023 | 2023-08-01 | 2023-10-01 | 61 | Ensure clarity, conciseness, and accuracy in depicting the target Data/AI roles in a concise and succinct one page format. | Completed; Hot Tasker from OPM 08/2023. Completed draft 09/2023 of one-pager vignettes. Received feedback 10/2023. Final vignettes submitted to OPM 11/2023. Need to update as work roles are refreshed. | Provided concise, one-page summaries of key Data/AI roles, enhancing clarity and understanding for OPM to aid in accurate and efficient position classification and talent management. | Completed - Requires periodic updates and maintenance | 95% - Need to update post Work Role refresh | Completed | 0.95 | 0 | Completed
0.9 | Work Role Coding / Competencies | 5.5.7.4 - Provide support for the Tech to Government working group related to data and AI. | DA&AI Position Description Development & Standardization | 10/2023 - 04/2024 | 2023-10-01 | 2024-04-01 | 183 | Standardize job descriptions for key digital roles to facilitate recruitment and hiring | Completed; Provided drafted generic templates to GPOC on 12/2023. Incorporated feedback and socialized with SMEs 01/2024 -03/2024/. De-prioritized effort 04/2024. | Standardized position description (PD) templates, incorporating Data/AI work roles and occupational series. This streamlined recruitment and hiring for key digital roles by providing clear, consistent, and OPM-compliant job descriptions. | Completed - Requires periodic updates and maintenance | 90% - Need to update post Competency Model creation | Completed | 0.9 | 0 | Completed
1 | Outreach & Engagement | 5.5.7.4 - Provide support for the Tech to Government working group related to data and AI. | Data Teams Playbook Development - Hiring for AI and AI-Enabling Talent | 12/2023 - 04/2024 | 2023-12-01 | 2024-04-01 | 122 | Provide best practices and resources to support the formation and operation of high-performing data teams. | Completed; Provided GPOC draft playbook on 02/2024. Incorporated feedback and provided final version to OPM 04/2024. OPM leverage and published Federal Playbook 08/2024 | Provided OPM with researched best practices and resources for building and managing high-performing data and AI teams to achieve mission-critical objectives. | Completed - Requires periodic updates and maintenance | 1 | Completed | 1 | 0 | Completed
1 | Research / Writing | 5.5.7.5 - Support the development of the Workforce Planning People Strategy. | Foreign National Talent Acquisition Strategy - Report to Address Gaps in AI Talent for National Defense | 01/2024 - 11/2024 | 2024-01-01 | 2024-11-01 | 305 | Develop a strategy to leverage foreign national talent to fill critical Data/AI skill gaps. | Completed; Drafted and coordinated with stakeholders from 01/2024 - 03/2024. Final draft provided 04/2024 to GPOC. Additional review request by I&S completed 06/2024. Final report submitted to CDAO Leadership 08/2024. | Provided the White House with critical recommendations for addressing the DoD's Data/AI talent gap by leveraging the expertise of foreign nationals, enhancing emerging technology competitiveness. | Completed | 1 | Completed | 1 | 0 | Completed
0.6 | Work Role Coding / Competencies | 5.5.7.1 - Support the data, analytics, and AI competency development and work role refresh. Create competency models for data, analytics, and AI. Leverage developed competencies to inform Work Role (KSAT) updates. | Data Competency Model Development | 10/2024 - Present | 2024-10-01 | 2025-11-01 | 396 | Define the key skills and knowledge required for success in Data roles. | Completed; Conducted industry research on data and AI competencies from 10/2024 - 01/2025. Provided drafted competency models to GPOC 02/2025. Updated competencies based on feedback 04/2025. Need to coordinate with DCPAS. | Provided a standardized framework for identifying, developing, and measuring expertise in Data, ultimately enhancing workforce capabilities and supporting mission success. | Mid Length (3-6 Months) | 60% - Competency Model drafted. Need to coordinate with DCPAS for SME sessions, Assessment and Final SME Validation Sessions | Long Term | 0.6 | 178 | In-progress
0.6 | Work Role Coding / Competencies | 5.5.7.1 - Support the data, analytics, and AI competency development and work role refresh. Create competency models for data, analytics, and AI. Leverage developed competencies to inform Work Role (KSAT) updates. | Analytics Competency Model Development | 10/2024 - Present | 2024-10-01 | 2025-12-01 | 426 | Define the key skills and knowledge required for success in Analytics roles. | Completed; Conducted industry research on data and AI competencies from 10/2024 - 01/2025. Provided drafted competency models to GPOC 02/2025. Updated competencies based on feedback 04/2025. Need to coordinate with DCPAS. | Provided a standardized framework for identifying, developing, and measuring expertise in Analytics, ultimately enhancing workforce capabilities and supporting mission success. | Mid Length (3-6 Months) | 60% - Competency Model drafted. Need to coordinate with DCPAS for SME sessions, Assessment and Final SME Validation Sessions | Long Term | 0.6 | 208 | In-progress
0.6 | Work Role Coding / Competencies | 5.5.7.1 - Support the data, analytics, and AI competency development and work role refresh. Create competency models for data, analytics, and AI. Leverage developed competencies to inform Work Role (KSAT) updates. | Artificial Intelligence Competency Model Development | 10/2024 - Present | 2024-10-01 | 2025-10-01 | 365 | Define the key skills and knowledge required for success in AI roles. | Completed; Conducted industry research on data and AI competencies from 10/2024 - 01/2025. Provided drafted competency models to GPOC 02/2025. Updated competencies based on feedback 04/2025. Need to coordinate with DCPAS. | Provided a standardized framework for identifying, developing, and measuring expertise in Artificial Intelligence, ultimately enhancing workforce capabilities and supporting mission success. | Mid Length (3-6 Months) | 60% - Competency Model drafted. Need to coordinate with DCPAS for SME sessions, Assessment and Final SME Validation Sessions | Long Term | 0.6 | 147 | In-progress
1 | Research / Writing | 5.5.7.1 - Support the data, analytics, and AI competency development and work role refresh. Create competency models for data, analytics, and AI. Leverage developed competencies to inform Work Role (KSAT) updates. | O*Net Job Family & Work Role Mapping | 12/2024 - Present | 2024-12-01 | 2025-12-01 | 365 | Integrate Data/AI roles into established job classification frameworks. | Completed; Researched Data/AI work roles externally from 12/2024 - 01/2025. Presented findings to GPOC 02/2025. Request for additional research. Need to complete crosswalk with work roles. | Ensured consistent classification of Data/AI roles by mapping them to established O*NET job families and series, supporting accurate workforce planning and talent management. | Completed - Needs Review and Approval | Completed | Completed | 1 | 208 | In-progress
0.5 | Work Role Coding / Competencies | 5.5.7.1 - Support the data, analytics, and AI competency development and work role refresh. Create competency models for data, analytics, and AI. Leverage developed competencies to inform Work Role (KSAT) updates. | Work Role Refresh & KSAT Validation for Data/AI Work Roles | 12/2024 - Present | 2024-12-01 | 2025-11-01 | 335 | Ensure that job requirements and selection criteria for Data/AI roles remain current and relevant. | Completed; Provided GPOC draft updates to all data work roles on 02/2024. Currently updating AI work roles completed on 04/2024. Need to assemble developmental SME panel to validate. | Modernized Data/AI work role descriptions and KSATs, ensuring accurate and effective talent acquisition and development strategies. This enhances the organization's ability to attract and select qualified candidates for critical emerging technology positions. | Long Term (6+ Months) | 50% - Need GPOC review and approval of recommendations. Need SME validation sessions, need to get CWMB approval, need to publish to DCWF | Long Term | 0.5 | 178 | In-progress
0 | Processes / Implementation | 5.5.7.3 - Collaborate with appropriate stakeholders to organize and execute Digital Talent Management Forum. | Cyber Workforce (CWF) Implementation Plan Support | 12/2023 - Present | 2023-12-01 | 2025-12-01 | 731 | Contribute to the successful implementation of the CIO's Cyber Workforce plan with supportive structuring, artifacts, and documentation. | Completed; Met with CIO for multiple CWF/ implementation plan initiatives. Currently awaiting meetings to be scheduled by CIO to continue implementation plan. | Enabled the effective execution of the CIO Cyber Workforce Implementation Plan by serving as the OCR POC, ensuring aligned communication and coordinated efforts across stakeholders, contributing to a more robust cyber workforce. | Long Term (6+ Months) | Continuous support to CIO as OCR | Long Term | 0 | 208 | In-progress
0 | Outreach & Engagement | 5.5.7.3 - Collaborate with appropriate stakeholders to organize and execute Digital Talent Management Forum. | Enterprise Talent Marketplace Pilot Participation | 06/2023 - 02/2024 | 2023-06-01 | 2024-02-01 | 245 | Contribute to the development and testing of a new talent management platform. | Completed; Researched alternative talent pool platforms from 06/2023 - 08/2023. Scheduled multiple demos between GPOC and vendors. Provided recommendations to adopt AVUE platform on 10/2023. Participated in TTX 01/2024. Put on Strategic Pause on 02/2024 | Contributed to the improvement of the Enterprise Talent Marketplace (ETM) pilot by identifying potential issues and opportunities during initial table-top exercises. | Completed | Continuous support to P&R/CTMO | Completed | 0 | 0 | Completed
1 | Outreach & Engagement | 5.5.7.3 - Collaborate with appropriate stakeholders to organize and execute Digital Talent Management Forum. | Data/AI Functional Community (FC) MilSuite Manager | 04/2024 - 04/2025 | 2024-04-01 | 2025-04-01 | 365 | Provide a single, authoritative source of information for the Data/AI FC on strategies, policies, and guidance related to digital talent, fostering collaboration and informed decision-making within the community. | Completed; Contributed to the design and stand up of DTM MilSuite page from 04/2024 - 06/2024. Continually added pertinent documents on strategies, memos, and other important correspondence on DoD wide platform from 06/2024 - 04/2025 | Ensured the accessibility and preservation of essential digital talent resources through the development, maintenance, and eventual migration of the Data/AI Functional Community MilSuite page, contributing to knowledge management and continuity within the organization. | Completed | Completed | Completed | 1 | 0 | Completed
1 | Outreach & Engagement | 5.5.7.3 - Collaborate with appropriate stakeholders to organize and execute Digital Talent Management Forum. | DA&AI FC - MilSuite Sunset Prep | 02/2025 - 04/2025 | 2025-02-01 | 2025-04-01 | 59 | Created location and structuring for all artifacts and documents previously housed on sunsetting MilSuite for continuity, institutional knowledge and document preservation, and centralized access since MilSuite could no longer be used/accessible. Moved all documents and artifacts from MilSuite to new internal location. | Internal location structure is complete. Relocation of all documents and artifacts previously housed on MilSuite is complete. | All files previously held on MilSuite, as opposed to being lost when it was sunset, are now preserved for central accessibility, logical restructuring, continuity, institutional knowledge and document preservation, and protection of government assets. | Completed | Completed | Completed | 1 | 0 | Completed
0.5 | Work Role Coding / Competencies | 5.5.7.1 - Support the data, analytics, and AI competency development and work role refresh. Create competency models for data, analytics, and AI. Leverage developed competencies to inform Work Role (KSAT) updates | Data/AI Work Role Code Assignment Tool | 07/2024 - 10/2024 | 2024-07-01 | 2024-10-01 | 92 | Deploy a user-friendly decision support tool that enables consistent and accurate assignment of data/AI work role codes by business system owners and supervisors Department-wide. | Completed; Presented process mapping to GPOC on decision tree tool on 09/2024. Tool development put on strategic pause 10/2024 due to resources. | Migrated all DA&AI FCM and CDAO DTM documents and artifacts from the decommissioned MilSuite platform to a new internal location, ensuring continued access, preserving institutional knowledge, and centralizing resources. | Long Term (6+ Months) | 50% - Decision Tree mapped out, need approval and need resources to develop functional tool. | Long Term | 0.5 | 0 | Completed
1 | Data | 5.5.7.2 - Create, iterate, and publish guidance materials for the data/AI and work role coding guide | Digital Workforce Data Enhancement | 06/2023 - 06/2024 | 2023-06-01 | 2024-06-01 | 366 | Provide reliable data insights for effective management of the DoD's digital workforce, enabling informed decision-making in recruitment, retention, and training. | Completed ; 10/2023 - 06/2024. Conducted numerous data refresh and updates to data fields for dashboard development. On 12/2023, presented recommendation to ensure clean data. | Enhanced DoD digital workforce data, through inventory refresh, a new Research & Analysis program, data integration, training data identification, and validation, empowers effective management and optimizes recruitment, retention, and training strategies. | Completed - Requires periodic updates and maintenance | Completed | Completed | 1 | 0 | Completed
0.5 | Processes / Implementation | 5.5.7.6 -Support the development of a DoD Digital Talent Awards Program | Data, Analytics, & AI Excellence Awards Program | 10/2024 - 12/2024 | 2024-10-01 | 2024-12-01 | 61 | Establish and implement a DoD awards program fostering a data-driven culture by recognizing individuals and teams demonstrating excellence in data, analytics, and AI. | Completed draft of Awards Announcement Memo on 05/2024. Developed a MS Form to capture nominees. Setup Awards mailbox for central communications across DoD on 06/2024. | Promoted a data-driven culture by recognizing and incentivizing excellence and innovation in data, analytics, and AI solutions. | Long Term (6+ Months) | 50% - Initial draft complete. Need to modify POAM, need GPOC approval and collaboration with MilDeps and 4th Estate stakeholders | Long Term | 0.5 | 0 | Completed
0.9 | Data | 5.5.7.2 Create, iterate, and publish guidance materials for the data/AI and work role coding guide | Work Role Coding Dashboard Enhancement | 10/2023 - Present | 2023-10-01 | 2024-12-01 | 427 | Enhance the WRC dashboard to provide timely and accurate Data & AI workforce metrics by leveraging automated data feeds and validated data sources. | Analytics team has been decommissioned as of 04/2025. Need to resume development and maintenance of dashboard. | Automated data updates and a redesigned backend architecture enhance the Work Role Coding Dashboard, providing timely and accurate Data & AI WRC progress metrics. | Completed - Requires periodic updates and maintenance | 90% - Need to continue refinement and development of dashboard. Need colloborative efforts with R&E and CIO. | Completed | 0.9 | 0 | Completed
0.9 | [6 empty] | 0 |  |  |  | Completed - Needs Review and Approval | 90% - Need to continue refinement and development of dashboard. Need colloborative efforts with R&E and CIO. | Completed | 0.9 | 0 | Completed
0.75 | Strategy | 5.5.7.5 Support the development of the Workforce Planning People Strategy. | CDAO People Strategy | 08/2024 - 01/2025 | 2024-08-01 | 2025-01-01 | 153 | Establish a robust and future-ready Data, Analytics, and AI (DA&AI) workforce capable of meeting the evolving mission needs of the Department. | Strategic Pause | Coordinated strategy to address critical staffing, skills, and cultural gaps within the Department's Data, Analytics, and AI workforce, guiding talent acquisition, development, and retention to achieve strategic objectives. | Mid Length (3-6 Months) | 75% - Initial draft complete. Need to modify POAM, need GPOC approval and collaboration with MilDeps and 4th Estate stakeholders | Long Term | 0.75 | 0 | Completed
0.9 | Strategy | 5.5.7.5 Support the development of the Workforce Planning People Strategy. | DTM FCM Workforce Planning | 01/2025-02/2025 | 2025-01-01 | 2025-02-01 | 31 | Initialize update to draft People Strategy and incorporate tactical implementation consideration factors, broken down by key milestones and supporting tasks, to trace overarching strategic goals and objectives into programmatic-level activities | Continuous Effort: Strawman of People Strategy Refresh and Redirection was delivered on 4 Feb 2025, efforts have continued to highlight additional considerations to be incorporated into the next draft of the overarching People Strategy | Documented "top-down" and "bottom-up" correlations and advanced planning for overarching People Strategy strategic goals and objectives to iterative milestones, then to programmatic, tactical actions and activities for achievement of the People Strategy, allowing for measurement toward this accomplishment over time and program-level direction guided by the established strategic goals and objectives. | Completed - Requires periodic updates and maintenance | 90% - Need GPOC approval to update roadmap per the new redirection | Completed | 0.9 | 0 | Completed
0 | Outreach & Engagement | 5.5.7.3 - Collaborate with appropriate stakeholders to organize and execute Digital Talent Management Forum. | Community Engagement & Outreach - Digital Talent Management Forum (DTMF) Representation & Leadership | 08/2023 - Present | 2023-08-01 | 2025-11-01 | 823 | Gather and disseminate knowledge on digital workforce management trends and strategies | Continuous Efforts; KGS participated in 18+ Monthly engagements with tri-chair members that include pre-planning, agenda brainstorming and securing of briefers. | Fostered knowledge exchange on digital workforce best practices, strengthening the Department's ability to attract and retain top digital talent. | Completed - Requires periodic updates and maintenance | Continuous support as a Tri-Chair member with R&E and A&S | Completed | 0 | 178 | In-progress
0 | Outreach & Engagement | 5.5.7.3 - Collaborate with appropriate stakeholders to organize and execute Digital Talent Management Forum. | Community Engagement & Outreach - Digital Talent Management Forum (DTMF) Involvement | 08/2023 - Present | 2023-08-01 | 2025-11-01 | 823 | Keep other DTMF members and entities informed of CDAO and DA&AI priorities, timelines, and progress; assist other Forum members in understanding and incorporating CDAO and DA&AI activities and plans into their own portfolios and timelines; Complete similar assessment for inputs of other Forum members; assessed impact of other Forum members portfolios, efforts, timelines, strategic alignment, and their presentations/statuses on CDAO portfolio | Documentation and artifacts created for each instance of the DTMF, including information shared and impact, and information received and impact | Created a holistic collection of progress throughout the evolution of DTMF-related content both in CDAO and DA&AI functional community portfolios, which then could be referenced for prioritization and timing of portfolio elements. Also in providing this information about CDAO and DA&AI functional community to other DTMF members, created a bi-directional information and prioritization flow to maximize coordination, reduce duplication, and benchmark work planned/completed; Kept GPOC and CDAO/DA&AI Functional Community members aware of this coordinated approach to portfolio review and impact | Completed - Requires periodic updates and maintenance | Continuous support as a Tri-Chair member with R&E and A&S | Completed | 0 | 178 | In-progress
0.9 | Strategy | 5.5.7.5 Support the development of the Workforce Planning People Strategy. | Strategic Portfolio Roadmap - DTM FCM Governance Portfolio | 07/2024 - Present | 2024-07-01 | 2025-10-01 | 457 | Support DTM FCM colleagues with continuous build out, update, and refresh of DA&AI Governance portfolio effort with a visual representation of key portfolio attributes and work products, including objectives, timeline, milestones, and challenges and risks | - Established Q1 FY2025 | Vision of the DTM FCM Governance Portfolio as outlined on the Strategic Portfolio Roadmap via 7 milestones through April 2026 was to pioneer a transformative governance structure, centralized in policy, decentralized in execution, and aligned with DoDI 1400.25 Vol 250 Civilian Strategic Human Capital Planning. Highlights milestones necessary to empower military and civilian workforce, fostering a collaborative ecosystem where Component Integrators (CIs)--both HR and manpower professionals--work synergistically. | Completed - Needs Review and Approval | 90% - Need GPOC approval to update roadmap per the new redirection | Completed | 0.9 | 147 | In-progress
0.9 | Strategy | 5.5.7.1 - Support the data, analytics, and AI competency development and work role refresh. Create competency models for data, analytics, and AI. Leverage developed competencies to inform Work Role (KSAT) updates. | Strategic Portfolio Roadmap - DA&AI Competency Model and Work Role Refresh Portfolio Roadmap | 07/2024 - Present | 2024-07-01 | 2025-10-01 | 457 | Lead the continuous build out, update, and refresh of the DA&AI Competency Model and Work Role Refresh Portfolio with a visual representation of key portfolio attributes and work products, including objectives, timeline, milestones, and challenges and risks | - Established Q1 FY2025 | Vision across 7 milestones through Dec 2025 is to develop three distinct Competency Models for 1) Data, 2) Analytics, and 3) Artificial Intelligence to ensure an accurate reflection of the current demands, align with the organization’s mission, and support effective performance and development and inform updates the DA&AI Work Role Knowledge, Skills, Abilities, and Tasks (KSATs) | Completed - Needs Review and Approval | 90% - Need GPOC approval to update roadmap per the new redirection | Completed | 0.9 | 147 | In-progress
0.9 | Strategy | 5.5.7.5 Support the development of the Workforce Planning People Strategy. | Strategic Portfolio Roadmap - People Strategy | 07/2024 - Present | 2024-07-01 | 2025-11-01 | 488 | Lead the continuous build out, update, and refresh of the DA&AI FCM People Strategy Portfolio with a visual representation of key portfolio attributes and work products, including objectives, timeline, milestones, and challenges and risks | - Established Q2 FY2025 | As a key DTM FCM Workforce Planning roadmap, value added is to augment DTM FCM development of a 5 year People Strategy representative mission owner needs (Army, Navy, Air Force) serving as the “north star” to ensure staffing, skills, and culture gaps within the DA&AI workforce are reduced to risk levels acceptable to the Functional Chief (in collaboration with Component Functional Community Managers (CFCMs). | Completed - Needs Review and Approval | 90% - Need GPOC approval to update roadmap per the new redirection | Completed | 0.9 | 178 | In-progress
0.9 | Strategy | 5.5.7.5 Support the development of the Workforce Planning People Strategy. | Strategic Portfolio Roadmap - Decision Support Tool | 07/2024 - 10/2024 | 2024-07-01 | 2024-10-01 | 92 | Lead the continuous build out, update, and refresh of the DA&AI FCM Decision Support Tool Portfolio with a visual representation of key portfolio attributes and work products, including objectives, timeline, milestones, and challenges and risks | - Established Q4 FY2024 - Paused in mid Dec 2024 due to APL's departure | Objective is to design and develop a decision support tool to enhance business systems owners and supervisor decision-making. | Completed - Needs Review and Approval | 90% - Need GPOC approval to update roadmap per the new redirection | Completed | 0.9 | 0 | Completed
0.9 | Strategy | 5.5.7.5 Support the development of the Workforce Planning People Strategy. | Strategic Portfolio Roadmap - DA&AI Awards | 07/2024 - Present | 2024-07-01 | 2025-11-01 | 488 | Lead the continuous build out, update, and refresh of the DA&AI Awards Portfolio with a visual representation of key portfolio attributes and work products, including objectives, timeline, milestones, and challenges and risks | - Established Q2 FY2025 | DTM-FCM develops and establishes an awards program for Excellence in DA&AI to create a digital culture that strives for excellence by recognizing individuals and teams who accept informed risk to rapidly deploy agile, innovative solutions while embracing collaboration across institutional boundaries across DOD boundaries in FY 2025. | Completed - Needs Review and Approval | 90% - Need GPOC approval to update roadmap per the new redirection | Completed | 0.9 | 178 | In-progress
0.9 | Strategy | 5.5.7.5 Support the development of the Workforce Planning People Strategy. | Strategic Portfolio Roadmap - CDAO Work Role Coding | 07/2024 - Present | 2024-07-01 | 2025-09-01 | 427 | Lead the continuous build out, update, and refresh of the CDAO Work Role Coding Portfolio with a visual representation of key portfolio attributes and work products, including objectives, timeline, milestones, and challenges and risks | - Established Q4 FY2024 - To date: Milestone 4 initiated: Begin Coding, Distribute and DCPDS data (spreadsheets) and WRC guidance via CATMS | Initiate pilot to evaluate effectiveness of Work Role Coding (WRC) guidance material, methodology, and stakeholder engagement, in order to proactively identify and address any unanticipated challenges prior to implementing the Department of Defense (DoD) enterprise-wide coding initiative. | Completed - Needs Review and Approval | 90% - Need GPOC approval to update roadmap per the new redirection | Completed | 0.9 | 117 | In-progress
0.9 | Strategy | 5.5.7.5 Support the development of the Workforce Planning People Strategy. | Strategic Portfolio Roadmap - “Go Code” Military Work Roles | 07/2024 - Present | 2024-07-01 | 2025-11-01 | 488 | Support DTM FCM colleagues with continuous build out, update, and refresh of "Go Code" Military-specific work role effort Portfolio with a visual representation of key portfolio attributes and work products, including objectives, timeline, milestones, and challenges and risks | - Established Q3 FY2024 | Each MILDEP and DAFAs has coded military workforce across HR and Manpower systems, providing CDAO the ability to report metrics on the DoD Data/AI military workforce with confidence by the end of FY 2025; CDAO has initiated transition of the pilot program to sustainment. | Completed - Needs Review and Approval | 90% - Need GPOC approval to update roadmap per the new redirection | Completed | 0.9 | 178 | In-progress
0.9 | Strategy | 5.5.7.5 Support the development of the Workforce Planning People Strategy. | Strategic Portfolio Roadmap - “Go Code” Civilian Work Roles | 07/2024 - Present | 2024-07-01 | 2025-12-01 | 518 | Support DTM FCM colleagues with continuous build out, update, and refresh of "Go Code" Civilian-specific work role effort Portfolio with a visual representation of key portfolio attributes and work products, including objectives, timeline, milestones, and challenges and risks | - Established Q1 FY2024 - To date: Milestone 3 initiated: Components respond with coding FC POCs and begin coding. | Each Component and DAFAs has coded their civilian workforce across the HR and Manpower systems, providing CDAO the ability to report metrics on the DoD Data/AI civilian workforce with confidence NLT the end FY 2025, and CDAO has started activities for a transition to sustainment. Goal is to provide CDAO the ability to report metrics on the DoD Data/AI civilian workforce with confidence by the end of FY 2025 | Completed - Needs Review and Approval | 90% - Need GPOC approval to update roadmap per the new redirection | Completed | 0.9 | 208 | In-progress
0.65 | Outreach & Engagement | 5.5.7.1 - Support the data, analytics, and AI competency development and work role refresh. Create competency models for data, analytics, and AI. Leverage developed competencies to inform Work Role (KSAT) updates. | Community Engagement & Outreach - USD(P&R) On-site Work Role Coding Workshop | 08/2024 - Present | 2024-08-01 | 2025-11-01 | 457 | Establish standardized descriptions and codes for these roles, facilitating consistent terminology, competency mapping, improved recruitment and hiring, targeted career development, informed workforce planning, and enhanced interoperability across the Department of Defense. | Participating as Action Officer in P&R Functional Community meetings. | Create a standardized, Department-wide understanding of critical emerging technology work roles, ultimately leading to more effective talent management, streamlined recruitment and hiring processes, targeted professional development initiatives, and data-driven workforce planning to support mission readiness. This standardization also improves interoperability and communication across DoD components, enabling better collaboration and resource allocation. | Completed - Requires periodic updates and maintenance | Continuous support to P&R | Completed | 0.65 | 178 | In-progress
0.55 | Outreach & Engagement | 5.5.7.3 - Collaborate with appropriate stakeholders to organize and execute Digital Talent Management Forum. | Community Engagement & Outreach - DA&AI FCM Action Officer (AO) Working Group | 06/2024 - Present | 2024-06-01 | 2025-11-01 | 518 | Cultivate a robust data and AI talent pool across the DoD by fostering collaboration and knowledge sharing, including resources, best practices, and internal guidance, ensuring the Department's current and future data and AI workforce needs are met. | Consistent support for governance activities, such as meeting facilitation and resource development, further enhancing the effectiveness and impact of the Data and AI Functional Community. Need new GPOC to continue with monthly FC AO meetings. | Strengthen the DoD's data and AI talent pipeline through collaborative knowledge sharing and resource development, ensuring the Department is equipped to meet current and evolving mission needs. | Continuous Collaboration Efforts | Continuous effort to lead monthly AO meetings to share Data/AI Initiatives | Continuous | 0.55 | 178 | In-progress
0.8 | Outreach & Engagement | 5.5.7.4 -Provide support for the Tech to Government working group related to data and AI | Community Engagement & Outreach - OPM Tech to Gov Working Group | 10/2023 - 12/2024 | 2023-10-01 | 2024-12-01 | 427 | Transform Federal government recruitment, hiring, and retention strategies for technology, cybersecurity, and AI talent, making government service a more attractive and competitive career path. | Participated as Action Officer during monthly working group engagements. OPM has paused efforts and working group due to resources. | Ensured that the unique needs and perspectives of the Department of Defense regarding data and AI talent are incorporated into federal government-wide strategies for attracting, hiring, and retaining top technology talent. This collaboration strengthens the DoD's ability to compete for critical skills in these fields. | Continuous Collaboration Efforts | Continuous support to OPM | Continuous | 0.8 | 0 | Completed
1 | Outreach & Engagement | 5.5.7.3 - Collaborate with appropriate stakeholders to organize and execute Digital Talent Management Forum. | Community Engagement & Outreach - Cyber Workforce Management Board (CWMB) | 06/2024 - Present | 2024-06-01 | 2025-10-01 | 487 | Integrate data and AI workforce development needs into the broader cybersecurity workforce strategy, ensuring alignment between these critical areas and strengthening the overall cybersecurity posture of the DoD. | Quarterly attendance with GPOC. Currently attendance paused until new GPOC. | Strengthen the DoD's overall cybersecurity posture by recognizing the crucial intersection of data/AI skills and cybersecurity expertise. Integrating data/AI workforce development into the broader cybersecurity strategy ensures a more comprehensive and effective approach to talent management, equipping the DoD with the integrated skillsets needed to address evolving cyber threats. | Continuous Collaboration Efforts | Completed | Continuous | 1 | 147 | In-progress
0.75 | Outreach & Engagement | 5.5.7.1 - Support the data, analytics, and AI competency development and work role refresh. Create competency models for data, analytics, and AI. Leverage developed competencies to inform Work Role (KSAT) updates. | Community Engagement & Outreach - DHRA/DCPAS Competency Model Coordination, Engagement, and Build | 10/2024 - 04/2025 | 2024-10-01 | 2025-04-01 | 182 | Collaborate with DCPAS to align on competency model development and implementation for data/AI work roles, including defining key skills and abilities (KSATs), establishing timelines for work role refresh and competency development, and outlining future collaborative efforts. | Weekly meetings from 10/2024 - 04/2025. Put on pause until new GPOC direction forward. Need to re-establish relationship with DCPAS leadership to gain buy-in and support. | Enhance the DoD's data/AI workforce by clarifying work role requirements, developing robust competency models, and ultimately improving talent acquisition and development strategies through a validated approach. This will ensure the department has the right skills to meet current and future data and AI challenges. | Mid Length (3-6 Months) | 75% - Need GPOC approval and continuous collaboration with DCPAS | Long Term | 0.75 | 0 | Completed
0.75 | Research / Writing | 5.5.7.5 Support the development of the Workforce Planning People Strategy. | HR Trending Deep Research & Analysis (Part 1) | 03/2025 - Present | 2025-03-01 | 2025-10-01 | 214 | In a briefing-ready, display style primed for voice track overlay, produce a robust, cross-references and generated view of HR trending in 2025 per the most influential research and source data organizations, thus creating both a goal- and self-measurement-oriented view of HR focus areas for growth and professional expression across the organization. | Delivered to GPOC on 3/18/2025, have not yet received any review notes, confirmation, or feedback for additional iterations or delivery | Prepared for briefings, discussions, and working groups related to HR talent and HR impact on overarching workforce or people strategy. Offers both tactical options for evolving HR talent across the CDAO and beyond, and strategic understanding of HR professionals' impact on other element of workforce strategy and strategic workforce planning. | Completed - Needs Review and Approval | 75% - Need GPOC approval and socialize with DA&AI FC for gap analysis | Completed | 0.75 | 147 | In-progress
0.75 | Research / Writing | 5.5.7.5 Support the development of the Workforce Planning People Strategy. | HR Trending Deep Research & Analysis (Part 2) | 03/2025 - Present | 2025-03-01 | 2025-12-01 | 275 | In a self-contained report style, produce a robust, cross-references and generated view of HR trending in 2025 per the most influential research and source data organizations, thus creating both a goal- and self-measurement-oriented view of HR focus areas for growth and professional expression across the organization. | Delivered to GPOC on 3/18/2025, have not yet received any review notes, confirmation, or feedback for additional iterations or delivery | Designed to be a sharable, self-contained research-brief to accompany an email or as a meeting take-away. Offers both tactical options for evolving HR talent across the CDAO and beyond, and strategic understanding of HR professionals' impact on other element of workforce strategy and strategic workforce planning. | Completed - Needs Review and Approval | 75% - Need GPOC approval and socialize with DA&AI FC for gap analysis | Completed | 0.75 | 208 | In-progress
0.75 | Research / Writing | 5.5.7.5 Support the development of the Workforce Planning People Strategy. | Data Analysis & AI Professional Criteria and Potential Mapping research & analysis | 03/2025 - Present | 2025-03-01 | 2025-11-01 | 245 | Deliver a mutli-layered competency and proficiency level mapping to Data & AI professionals, including professional certifications, education, and occupational series for the purpose of gaining a deeper understanding of the overlapping components of this competency based management and to offer a product that, when finalized, can be shared with a broader audience in the DA&AI functional community, and can be incorporated into/inform the update to the DA&AI FCM People Strategy | Research conducted across multiple, layered factors of competencies and proficiency levels, including professional certification, typical roles and career mapping/pathing, primary and secondary occupational series alignment, and educational alignment. Report is drafted but has not yet been reviewed, and can be fleshed out further or aligned with other documentation | Multifactored research and subsequent layering, with a basis grounded in common competencies and proficiency levels, gives a mappable view of DA&AI capabilities within an organization or functional community--mapping is the first step to understanding current capabilities, future mission-aligned needed capabilities, and the gap that exists between (e.g., like a fit-gap analysis). Thus and in line with the draft charter, this research and document provides the next step in tying multiple efforts together in a digestible, usable format for functional community components. | Completed - Needs Review and Approval | 75% - Need GPOC approval and socialize with DA&AI FC for gap analysis | Completed | 0.75 | 178 | In-progress
0.75 | Governance / Charter | 5.5.7.3 - Collaborate with appropriate stakeholders to organize and execute Digital Talent Management Forum. | DA&AI Functional Community Charter | 06/2023 - Present | 2023-06-01 | 2025-10-01 | 853 | Create a formally documented, accepted, and endorsed DA&AI Functional Community and Functional Community Manager authoritative record, inclusive of DA&AI FC/FCM mission, vision, guiding principles, authority, scope, methods, body of work, role and responsibilities, governance, decision making, and alignment with authoritative sources, including DoDI 1400.25 Vol. 250 | Most recent update to the charter (including version aligned point-by-point with DoDI 1400.25 Vol.250 and other FCM charters) delivered to GPOC on 4/17/2025. Prior version represent iterative construct and interaction with internal working groups on essential elements of FCM roles and responsibilities, scope, and governance construct | Formally documents and endorses DA&AI Functional Community and Functional Community Manager mission, vision, guiding principles, authority, scope, methods, body of work, role and responsibilities, governance, decision making, and alignment with authoritative sources, including DoDI 1400.25 Vol. 250 | Continuous Collaboration Efforts | 75% - Need GPOC approval and coordination with CDAO Front Office | Continuous | 0.75 | 147 | In-progress
0.75 | Governance / Charter | 5.5.7.3 - Collaborate with appropriate stakeholders to organize and execute Digital Talent Management Forum. | DA&AI Functional Community Governance Framework - Executive Overview | 03/2025 - Present | 2025-03-01 | 2025-12-01 | 275 | Provide a high level governance framework and overview designed for executive level consumption and understanding during a live briefing. Voice track is maximized while slides provide supplementary information and backdrops to the focus of the discussion. | Delivered to GPOC on 3/18/2025, continuous iterations to coordinate with evolution of DA&AI Functional Community Charter | Creates a beneficial style of presenting collective efforts in governance and future plans that are maximized in delivery by focusing on discussion and voice track as opposed to merely self-contained slide details. Structure, flow, and format encapsulates high-level, executive view-appropriate overviews while highlighting key factors for further questions and knowledge transfer/understanding. | Completed - Requires periodic updates and maintenance | 75% - Need GPOC approval and socialize with DA&AI FC for gap analysis | Completed | 0.75 | 208 | In-progress
1 | Processes / Implementation | 5.5.7.5 Support the development of the Workforce Planning People Strategy. | Portfolio Objectives and Key Results Development | 10/2023 - 10/2024 | 2023-10-01 | 2024-10-01 | 366 | Effectively manage and track the DTM-FCM project portfolio, ensuring successful execution and alignment with strategic objectives through diligent JIRA management, OKR tracking, and proactive collaboration with stakeholders to identify and address roadblocks. | Attended daily stand ups, weekly, monthly sprint planning and quarterly JIRA meetings to discuss progression. Project Management process eliminated on 10/2024. Critical that a formal project tracking method be implemented. | Ensures successful execution of the DTM-FCM portfolio, maximizing its impact on strategic objectives through proactive risk mitigation, continuous progress tracking, and transparent communication with stakeholders. | Completed | Completed | Completed | 1 | 0 | Completed
1 | [10 empty] | Completed | Completed | Completed | 1 | 0 | Completed
0.9 | Research / Writing | 5.5.7.2 Create, iterate, and publish guidance materials for the data/AI and work role coding guide | Development of Supplemental Guidance Materials Based on User Research and Analysis | 09/2023 - 11/2023 | 2023-09-01 | 2023-11-01 | 61 | Develop and iteratively refine supplemental guidance materials for data/AI work-role coding across the DoD Enterprise, based on insights gathered from Pilot 1 with DFAS, ultimately improving the accuracy and effectiveness of the coding process and increasing buy-in from stakeholders. | Completed a comprehensive analysis of interviews conducted on 11/2023. This analysis was delivered to the GPOC and subsequently presented, along with key findings and recommendations, to the entire DTM team at the quarterly on-site meeting on 01/2024. | Data-driven insights from user interviews shaped the development of targeted supplemental guidance materials, enhancing usability and addressing key user needs while ensuring privacy. | Completed - Requires periodic updates and maintenance | 90% - Continuous updates and iterations needed as work role coding effort moves forward | Completed | 0.9 | 0 | Completed